## Schedule
Template: Project Schedule
| Project Title | Effort Estimate in XXX | Planned Start Date | Planned End Date | Resource
1 | Activity
1.1 | Task
1.1.1 | Sub Task
1.1.2 | Sub Task
1.1.3 | Sub Task |  |  | -
2 | Activity
2.1 | Task
2.1.1 | Sub Task
2.1.2 | Sub Task
2.1.3 | Sub Task
2.1.4 | Sub Task
2.2 | Task
2.2.1 | Sub Task
2.2.2 | Sub Task
3 | Activity
3.1 | Task
3.1.1 | Sub Task
3.1.2 | Sub Task
3.1.3 | Sub Task
The project schedule is a detailed plan of major project activities and tasks, and the planned start and end date for each task, and the resources allocated to each task.
Enter the Title of the Project.
Enter the Activities, Tasks and Sub-tasks for your project. Use outline numbering if desired.
This inforamtion is taken from your work breakdown structure.
Activity is the highest level of categorization. Tasks and sub-tasks are lower-lever breakdowns. Scheduling is done at the lowest level.
Example: 1. Initiate Project
1.1 Develop Proejct Charter
1.1.1 Define Scope
1.1.2 Define Requirements
Scheduling is done at the 1.1.1 Define Scope and 1.1.2 Define Requirements level.
For each task iand sub-task n the work breakdown structure enter:
-The estimated effort to complete the work and the unit XXX of measure of the estimate. Example unit measure: Days, Hours, Weeks etc.
- Enter the date the task is planned to start.
- Enter the date the task is planned to end.
Enter the name of the staff resource (one or many) assigned to the task. The staff resource could be entered as first names, last names, initals etc. Example: Peggy or Jones or rdk. If the staff resource is not known, enter the role that will be assigned to the task. Example: programmer, technical writer etc

## Network Diagram
Template: Network Diagram
Project Title
Category | Category | Category | Category
The network diagram is a precendence diagramming method that identifies:
-the tasks that must be completed before other tasks can begin
-the tasks that can be done while other tasks are being performed
1.1
Task
2.1
Task
2.3
Task
3.1
Task
3.3
Task
3.4
Task
4
Task
2.2
Task
3.2
Task
Enter the title of the project.
Enter the major tasks from your work breakdown structure that you want to include in the network diagram. Use arrows to diagram the precedence of tasks and the tasks that can be done in parallel.
Optionally categorize or group the tasks at a higher level. Refer to your work breakdown structure for higher level organization.. Example: categories could be the project management stages - Initiate, Plan, Execute and Control, Close.

## Gantt Chart
Template: Gantt Chart
Project Title
|  | Label | [6 empty] | Label
|  | Unit of Time | Unit of Time | Unit of Time | Unit of Time | Unit of Time | Unit of Time | Unit of Time | Unit of Time
1 | Activity
1.1 | Task
2 | Activity
2.1 | Task
2.2 | Task
2.3 | Task
3 | Activity
3.1 | Task
3.2 | Task |  |  |  | ---- horizontal bar -----
3.3 | Task
3.4 | Task
4 | Activity
A Gantt chart graphically represents a project by showing each task as a horizontal bar whose length is the time needed to complete the task.
Enter the title of the project.
Enter the Activities, Tasks and Sub-tasks for your project. Use outline numbering if desired. Enter the level of detail you wish to display in the Gantt Chart - for communciation purposes the Gantt chart could show a high-level rollup of tasks.
This informaion is taken from your proejct schedule..
Enter the unit of time for the timeline. Example: day, month, week year etc.
Enter any other label that gives more information about the time frame displayed in the Gantt chart. Example: If the unit of time is Month, the label could be the year (2006) or the label could indicate quarters of a year (QTR 1) etc.Enter what makes sense for the project and what helps clarify the information being presented.
Enter the horizontal bars to indicate the length of time needed to complete the task.